## Sheet1
Sreen |  | Task | Time (hourse) | Start date | End date | Complete
Splash |  | Layout | 1 | 2021-08-14
|  | Implement check login | 1
Login | Login | Layout | 1
|  | Implement login processing | 2
| Register | Layout | 1
|  | Implement register processing | 1
| Forgot password | Layout | 1
|  | Implement register processing | 1
Main | Order | Layout | 2
|  | Get User Info | 1
|  | Get drink list | 1
|  | Display data | 2
|  | Handle selected item | 1
| Item detail | Layout | 1
|  | Display data | 2
|  | Handle order item | 1.5
| Order review | Layout | 2
|  | Display data | 3
|  | Handle pay processing | 2
| Vouchers | Layout | 1.5
|  | Display data | 2
| User Infor | Layout | 2
|  | Display data | 2
Total |  |  | 35